## Risks
Risk ID | Risk Category | Risk Description | Likelihood | Impact | Mitigation Strategy | Risk Owner | Comments/Status
R-001 | Security & Compliance | Sensitive data may be exposed during migration or in the new cloud environment, increasing the risk of data breaches and regulatory non-compliance. | High | Critical | Develop a phased migration plan with parallel run environments. Create detailed rollback and disaster recovery plans. Schedule migrations during offpeak hours. Perform premigration testing. | Security/Compliance Team | Continuous monitoring is required; consider third-party audits.
R-002 | Performance | Migration activities or misconfigurations may result in unexpected downtime affecting business operations. | Medium | High | Develop a phased migration plan with parallel run environments. - Create detailed rollback and disaster recovery plans. - Schedule migrations during off-peak hours. - Perform pre-migration testing. | IT Operations | Develop a comprehensive migration schedule and contingency plan.
R-003 | Data Migration/Integrations | Integration Challenges with Legacy Systems: Older legacy systems might not integrate seamlessly with modern cloud platforms, leading to functionality issues. | High | High | Conduct thorough system compatibility and integration testing. Develop custom API gateways or middleware solutions. Engage vendor support for legacy system integration. | Integration Team | Map out legacy dependencies early and consider refactoring where possible.
R-004 | Cost/Time/Resource | Cost Overruns: Unplanned costs may arise from underestimating migration complexity, unanticipated cloud service pricing, or inefficient resource utilization. | Medium | High | Perform a detailed cost analysis and budgeting exercise prior to migration. Monitor cloud spending in real time with cost management tools. Allocate a contingency budget for unexpected costs. | Finance/Project Manager | Regular financial reviews to adjust forecasts are advised.
R-005 | Skill & Training | Lack of Cloud Expertise/Training: Inadequate skills among team members may result in suboptimal configuration, deployment errors, or delayed migration timelines. | High | Medium | Invest in comprehensive cloud training and certification programs. Hire or consult with cloud migration experts. Establish a knowledgesharing platform internally. | HR/IT Leadership | Initiate training programs and consider a mentorship model.
R-006 | Security & Compliance | Compliance & Regulatory Risks: The new cloud environment may not meet data residency or industry-specific regulations, leading to legal and reputational issues. | Medium | Critical | Map regulatory requirements before migration. Collaborate closely with legal and compliance teams. Choose cloud providers with relevant certifications (e.g., ISO, SOC). | Compliance Team | Regular reviews against changing regulatory frameworks are necessary.
R-007 | Performance | Performance & Latency Issues: Applications may suffer from degraded performance or increased latency in the cloud environment. | Medium | High | Conduct extensive performance and load testing in a cloud pilot. Optimize applications for cloud architectures. Leverage autoscaling and load balancing features. | IT Operations/DevOps | Benchmark current performance and monitor continuously post-migration.
R-008 | Vendor | Vendor Lock-In: Over-dependence on a single cloud provider might reduce future flexibility and increase switching costs if requirements change. | Medium | Medium | Consider a multicloud or hybridcloud strategy where feasible. Emphasize open standards and containerization (e.g., Kubernetes). Negotiate clear exit strategies and SLAs in contracts. | Procurement/IT Strategy | Evaluate long-term vendor relationships periodically.
R-009 | Data Migration/Integrations | Data Migration Errors: Risks of data corruption, loss, or inconsistency during the migration process may occur. | Medium | High | Develop and test data migration scripts in a sandbox environment. Validate data integrity with multiple reconciliation processes. Schedule incremental migrations to minimize risk. | Data Management Team | Implement rollback strategies and backup procedures before migration.
R-010 | Data Migration/Integrations | Network Connectivity & Latency: Poor network connectivity or insufficient bandwidth could hinder data transfer speeds and affect application performance. | Medium | High | Upgrade network infrastructure or establish dedicated connections. Use content delivery networks (CDNs) and optimize network routing. Monitor network performance closely during migration. | Network Engineering | Ensure SLAs with connectivity providers are robust.
R-011 | Operations | Disaster Recovery and Business Continuity Failures: Inadequate disaster recovery plans can result in prolonged downtime and data loss in case of failures. | Medium | Critical | Develop, test, and regularly update disaster recovery and business continuity plans. Utilize geographically diverse data centers for redundancy. Automate backup processes and periodic restoration tests. | IT Operations/Business Continuity | Conduct regular disaster recovery drills to verify readiness.
R-012 | Security & Compliance | Unplanned Regulatory Changes: Sudden changes in regulations may impact cloud operations and require additional compliance measures post-migration. | Low | Critical | Stay updated with regulatory trends and consult industry experts. Build flexibility into the cloud architecture to adapt quickly to changes. Maintain an agile compliance review process. | Legal/Compliance Team | Regularly review and update policies in response to regulatory updates.
R-013 | Performance | Limited Scalability and Performance Bottlenecks: Inadequate planning for scalability might result in performance bottlenecks as usage grows. | Medium | High | Architect cloud solutions with scalability in mind (e.g., microservices, autoscaling groups). Conduct capacity planning exercises and stress tests. Monitor and optimize resource allocation continuously. | IT Architecture/DevOps | Scale resources dynamically based on load and forecasted demand.
R-014 | Skill & Training | Organizational Resistance to Change: Internal resistance from staff or stakeholders due to unfamiliarity with new cloud processes and tools. | Medium | Medium | Communicate benefits and impacts clearly to all stakeholders. Involve key personnel early in the migration planning process. Provide comprehensive training and support during and after migration. | Change Management/HR | Develop an internal change management strategy with clear milestones.
R-015 | Operations | Inadequate Monitoring and Logging: Lack of comprehensive monitoring tools might delay detection of issues post-migration. | Medium | High | Deploy centralized monitoring and logging solutions (e.g., CloudWatch, Splunk). Set up alerting and automated remediation where possible. Regularly review logs and performance metrics. | IT Operations/DevOps | Continuously refine monitoring strategies based on post-migration performance.

## Lists
Security & Compliance
Operations
Data Migration/Integrations
Cost/Time/Resource
Skill & Training
Secutiy & Compliance
Vendor
Performance