## Data Sprints
Sprint | Task | Datasets | Checks | Validation Steps
Sprint 1 | Foundational Data & Organizational Structures | 1. Employee Master Data (profiles, IDs, contact information); 2. Organizational Units (departments, divisions, cost centers); 3. Locations & Regional Data | Ensure that every employee record is accurately linked to the correct department and location; Validate data integrity using counts and cross-references with PeopleSoft records. | Pre-migration: Verify schema, mandatory fields, and uniqueness constraints; Post-migration: Compare total record counts and perform spot-check validations.
Sprint 2 | Recruitment Metadata & Configurations | 4. Job Requisition Templates; 5. Job Positions & Profiles; 6. Candidate Source Configurations (job boards, referral channels) | These metadata elements are critical as they drive the recruitment process; Ensure that mappings (e.g., job codes, role hierarchies) are accurate. | Validate configurations against PeopleSoft settings; Use checksum and control totals for each configuration group.
Sprint 3 | Candidate & Application Data (Part I) | 7. Active Candidate Applications; 8. Historical Candidate Records (segmented by application date or region to manage load) | Migrate in batches to handle load and avoid downtime; Ensure candidates are linked to corresponding job requisitions and positions established in Sprint 2. | Verify application dates, candidate statuses, and completeness of profiles; Reconcile batch-wise record counts with PeopleSoft.
Sprint 4 | Candidate & Application Data (Part II) – Transactional Data | 9. Interview Data (schedules, feedback, interviewer notes); 10.Offer Details (offer letters, negotiation history, acceptance/rejection statuses) | These datasets depend on candidate and job data from previous sprints; Validate that all relational links (e.g., candidate to interview, interview to offer) remain intact. | Run referential integrity checks to ensure no orphan records exist; Conduct end-to-end tests simulating the recruitment process in the target Workday system.
Sprint 5 | Reconciliation, Incremental Loads & Final Integration | 11. Incremental Updates (for any data changes that occurred during the initial sprints); 12. Audit Logs and Exception Records | Capture any updates that have occurred in PeopleSoft since the migration began, ensuring no data is missed; Final integration testing to confirm that all migrated datasets interact correctly. | Perform full-cycle reconciliation comparing PeopleSoft and Workday datasets; Utilize automated scripts to check 100% accuracy across data elements.